## Executive Summary
PULSE — UAE PILOT LAUNCH PLAN
Complete Cost Breakdown & Tech Stack — Demo to Live
COST SUMMARY
Category | Year 1 Cost (AED) | Monthly Run Rate | Notes
Development (MVP) | 55000 | 4583.3333 | 2 devs × 12 weeks
Infrastructure & Hosting | 2160 | 180 | Servers + CDN + domain
Video Infrastructure | 3600 | 300 | Jitsi self-hosted on Hetzner
Payment Gateway Setup | 500 | 0 | PayTabs onboarding (no monthly fee)
App Store Fees | 455 | 0 | Apple $99/yr + Google $25 one-time
SMS/Email Services | 2400 | 200 | AWS SNS + Resend
Content Moderation | 1200 | 100 | NSFWJS + Azure free tier
Legal & Business Setup | 19300 | 0 | Freezone license + visa
Age Verification | 8000 | 0 | TRA compliance integration
Marketing (Pilot) | 15000 | 1250 | Influencer + launch events
Reserve / Contingency | 10000 | 0 | Buffer for unexpected costs
TOTAL YEAR 1 | 117615 | 6613.3333
KEY DECISION
Total ~AED 118K ($32K) to launch a functional UAE pilot.
This fits inside a $50K angel check or self-funded bootstrap.
The $2.5M raise is for scaling AFTER pilot proves traction.

## Tech Stack
TECH STACK COMPARISON — CHEAPEST VIABLE OPTIONS
Blue = input assumptions you can change ¦ Black = formulas ¦ Green = cross-sheet links
VIDEO / WEBRTC
Provider | Cost/Min/User | Monthly Est. | Free Tier | Recommendation
Jitsi (open source) | FREE | 14 | Unlimited | MVP — self-host on Hetzner €3.49/mo
LiveKit Cloud | $0.0004/min | 120 | Yes | Scale — best price/performance ratio
100ms | $0.004/min | 300 | 10K min free | Alternative — good docs, easy integration
Daily.co | $0.004/min | 300 | Yes | Expensive — skip
Agora | $0.99/1K min | 250 | 10K min free | Enterprise — overkill for pilot
PAYMENT GATEWAY (UAE/AED)
Provider | Transaction Fee | Monthly Fee | Setup Fee | Recommendation
PayTabs | 2.85% + AED 0.27 | FREE | FREE | BEST — MENA-native, cheapest, no monthly
Amazon Pay Svcs | 2.65% + AED 1.00 | FREE | FREE | Good — ex-Payfort, trusted in UAE
Tap Payments | 2.5-3.0% | TBD | FREE | Good — Apple Pay + mada support
Telr | 2.49% + AED 0.50 | AED 99 | AED 349 | Avoid — monthly fee kills unit economics
Stripe | 2.9% + AED 1.00 | FREE | FREE | Skip — most expensive per-transaction
BACKEND / DATABASE
Provider | Cost/Month | Free Tier | Best For | Recommendation
Pocketbase | FREE (self-host) | Unlimited | MVP <50K users | MVP — zero cost, SQLite, fast
Supabase | AED 92/mo (Pro) | 1GB + auth | Realtime + Auth | Scale — Postgres, realtime lobby
Neon Postgres | AED 18/mo | 100 CU-hrs | Serverless DB | Alternative — pay-per-use
Firebase | Pay-per-read | 50K reads/day | Mobile-first | Avoid — expensive at scale
Appwrite | FREE (self-host) | Unlimited | Full BaaS | Alternative — more features than Pocketbase
HOSTING
Provider | Cost/Month | Free Tier | Bandwidth | Recommendation
Cloudflare Pages | FREE | Unlimited | Unlimited | Frontend — free forever, global CDN
Hetzner CX22 | AED 14/mo | No | 20TB | Backend — best value VPS globally
Railway | AED 18/mo | Trial only | Pay-per-use | Alternative — managed, easy deploy
Vercel | FREE (hobby) | 100GB/mo | 100GB | Current demo — keep for now
Fly.io | AED 20+/mo | No free tier | Pay-per-use | Skip — removed free tier 2024
MODERATION & SAFETY
Provider | Cost/Month | Type | Accuracy | Recommendation
NSFWJS | FREE | Client-side JS | ~93% | MVP — runs in browser, zero cost
OpenAI Moderation | FREE | API (text) | High | Text moderation — free forever
Azure Content Safety | FREE (5K/mo) | API (image) | High | Image backup — free tier sufficient
Google Vision | AED 5.50/1K | API (image) | Very high | Scale — when volume exceeds free tiers
Hive Moderation | AED 550+/mo | Enterprise | Very high | Overkill — enterprise pricing
SMS & EMAIL
Provider | Cost/Message | Free Tier | UAE Support | Recommendation
AWS SNS | AED 0.018/SMS | N/A | Yes | SMS OTP — 10x cheaper than Twilio
Twilio | AED 0.40/SMS | N/A | Yes | Skip — expensive for UAE
Resend | FREE (<3K/mo) | 3K emails/mo | Yes | Email — free for pilot volume
Postmark | AED 55/mo | N/A | Yes | Alternative — premium deliverability
APP FRAMEWORK
Option | Dev Cost (AED) | Timeline | App Store | Recommendation
PWA (web app) | 55,000-92,000 | 8-10 weeks | No store needed | PHASE 1 — fastest to market, cheapest
Flutter | 92,000-150,000 | 12-16 weeks | iOS + Android | PHASE 2 — after PWA validates
React Native | 110,000-185,000 | 14-18 weeks | iOS + Android | Skip — bridge overhead hurts video
Native (Swift+Kotlin) | 185,000-370,000 | 20-28 weeks | iOS + Android | Skip — double the cost, double the time

## Development Roadmap
DEVELOPMENT ROADMAP — DEMO TO LIVE
12-week sprint plan for 2-person team (1 frontend, 1 backend)
Week | Phase | Deliverables | Frontend Dev | Backend Dev | Cost (AED) | Blockers / Dependencies
1-2 | Foundation | Auth, DB schema, user profiles, basic API | PWA setup, auth flows, profile UI | Pocketbase setup, API endpoints, auth | 9200 | Business license needed first
3-4 | Video Core | WebRTC integration, 1-to-1 calls, lobby system | Video UI, lobby queue, call controls | Jitsi deploy, signaling server, session mgmt | 9200 | Hetzner server provisioned
5-6 | Matching Engine | Swipe/discover, matching algo, 5×5 session logic | Discover screen, swipe UX, group session UI | Matching algorithm, session orchestration | 9200 | Video must be stable first
7-8 | Payments + Premium | PayTabs integration, session tickets, Premium tier | Payment flows, subscription UI, receipts | PayTabs webhooks, access control, billing | 9200 | PayTabs account approved
9-10 | Safety + Polish | Content moderation, reporting, age verification | Report UI, age gate, moderation dashboard | NSFWJS pipeline, report queue, TRA compliance | 9200 | TRA guidelines confirmed
11-12 | Launch Prep | Testing, soft launch, influencer onboarding | Performance audit, mobile polish, PWA install | Load testing, monitoring, backup systems | 9200 | 50 beta testers recruited
TOTAL |  |  |  |  | 55200
POST-LAUNCH (Month 4-6)
Phase | Deliverables | Cost (AED)
Flutter Native App | iOS + Android native apps (if PWA validates) | 55000
AI Matching v2 | Behavioral data → predictive matching | 18000
Content Engine | Auto-generated sharecards, Instagram stories | 9000
Analytics Dashboard | Retention, LTV, session metrics, investor reporting | 7000

## UAE Legal & Compliance
UAE LEGAL & COMPLIANCE CHECKLIST
Everything needed to legally operate a dating platform in the UAE
BUSINESS FORMATION
Item | Cost (AED) | Timeline | Notes
Freezone Trade License | 12500 | 2-4 weeks | Meydan or DSO (cheapest). Activity: IT Services / Digital Platform
Office / Flexi-desk (Year 1) | 5000 | Same day | Required for license. Shared desk sufficient for pilot
Founder Visa | 5500 | 2-3 weeks | Emirates ID + medical + insurance included
Corporate Bank Account | 0 | 1-2 weeks | ADCB or Mashreq. No minimum balance for startups
Domain (pulse.ae) | 300 | 1-2 days | Via .ae registrar. Reserve pulse.app too
Subtotal | 23300
REGULATORY COMPLIANCE
Requirement | Cost (AED) | Priority | Details
TRA Registration | 2000 | CRITICAL | Telecom Regulatory Authority. Video calling apps must register. Verify WebRTC is permitted.
Age Verification System | 8000 | CRITICAL | Federal Decree No. 26/2025. Must verify users are 18+. Use Emirates ID or third-party age gate.
UAE PDPL Compliance | 3000 | HIGH | Data Protection Law (Decree 45/2021). Privacy policy, consent flows, breach reporting. Penalty: up to AED 5M.
Content Moderation Policy | 1000 | HIGH | Written policy for TRA. Covers: nudity detection, hate speech, harassment, reporting mechanisms.
Terms of Service (Arabic + English) | 3000 | HIGH | Bilingual ToS required. Must comply with UAE Consumer Protection Law.
App Store Compliance (Apple) | 363 | MEDIUM | 17+ age rating. Content moderation proof. Privacy labels. Review can take 1-3 weeks for dating apps.
App Store Compliance (Google) | 92 | MEDIUM | Content rating questionnaire. Dating app policy compliance. Family policy exclusion.
Subtotal | 17455
KEY RISKS
VoIP RESTRICTION: UAE historically blocks VoIP (Skype, FaceTime). WebRTC in-browser may be treated differently. GET LEGAL OPINION BEFORE BUILDING.
CULTURAL SENSITIVITY: Dating apps are legal in UAE but marketing must be tasteful. Avoid explicit language. Frame as 'social connection platform.'
DATA RESIDENCY: UAE PDPL may require user data to be stored within UAE. Hetzner has no UAE datacenter. Consider AWS Bahrain (me-south-1).
PAYMENT COMPLIANCE: UAE Central Bank requires payment aggregators to be licensed. Using PayTabs/Stripe (licensed) covers this.

## Monthly Burn
MONTHLY BURN RATE — FIRST 12 MONTHS
Assumes launch at Month 3. Blue = adjustable inputs.
Expense | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
Development (2 devs) | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600
Hosting (Hetzner + CF) | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
Video Infra (Jitsi) | 14 | 14 | 14 | 14 | 50 | 100 | 200 | 300 | 400 | 500 | 600 | 700
Payment Gateway Fees | 0 | 0 | 0 | 200 | 400 | 600 | 800 | 1000 | 1200 | 1500 | 1800 | 2000
SMS/Email (AWS+Resend) | 0 | 0 | 50 | 100 | 150 | 200 | 250 | 300 | 350 | 400 | 450 | 500
Content Moderation | 0 | 0 | 50 | 100 | 100 | 100 | 150 | 150 | 200 | 200 | 250 | 300
Legal & Compliance | 10000 | 5000 | 2500 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0
Marketing | 0 | 0 | 5000 | 3000 | 2000 | 2000 | 1500 | 1500 | 1000 | 1000 | 1000 | 1000
Misc / Contingency | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500
TOTAL MONTHLY BURN | 19728 | 14728 | 17328 | 13628 | 12414 | 12714 | 8014 | 8364 | 8264 | 9214 | 9214 | 9614
CUMULATIVE SPEND | 19728 | 34456 | 51784 | 65412 | 77826 | 90540 | 98554 | 106918 | 115182 | 124396 | 133610 | 143224

## Launch Checklist
COMPLETE LAUNCH CHECKLIST
Every single thing that needs to happen to go live
Status | Task | Details | Cost (AED) | Week
LEGAL & BUSINESS
☐ | Register freezone company | Meydan Free Zone or DSO. Activity: IT Services / Digital Platform | 12500 | W1
☐ | Open corporate bank account | ADCB or Mashreq. Need trade license first | 0 | W2
☐ | Apply for founder visa | Emirates ID + medical + insurance | 5500 | W2
☐ | Register with TRA | Telecom Regulatory Authority — video calling compliance | 2000 | W1
☐ | Get legal opinion on WebRTC | Confirm browser-based video dating is compliant with UAE telecom law | 3000 | W1
☐ | Draft Terms of Service | Arabic + English. UAE Consumer Protection Law compliant | 3000 | W3
☐ | Draft Privacy Policy | UAE PDPL (Decree 45/2021) compliant | 0 | W3
☐ | Age verification integration | Federal Decree No. 26/2025 compliance | 8000 | W9
INFRASTRUCTURE
☐ | Provision Hetzner VPS | CX22 — €3.49/mo. Install Docker, Jitsi, Pocketbase | 14 | W1
☐ | Setup Cloudflare Pages | Migrate frontend from Vercel (or keep both) | 0 | W1
☐ | Deploy Jitsi Meet | Self-hosted on Hetzner. Test video quality from UAE | 0 | W3
☐ | Setup Pocketbase backend | User schema, session schema, match schema | 0 | W1
☐ | Configure AWS SNS | UAE phone number verification (OTP) | 50 | W2
☐ | Setup Resend email | Transactional emails — welcome, match notifications | 0 | W2
☐ | Register pulse.ae domain | Via UAE registrar. Point to Cloudflare | 300 | W1
PAYMENTS
☐ | Apply for PayTabs merchant account | KYC docs needed. 3-5 business days approval | 0 | W1
☐ | Integrate PayTabs SDK | Session tickets (AED 75), Premium (AED 199/mo) | 0 | W7
☐ | Test AED payments end-to-end | Sandbox → production. Apple Pay if available | 0 | W8
DEVELOPMENT
☐ | Auth system (phone + social) | Pocketbase auth + phone OTP via AWS SNS | 0 | W1-2
☐ | User profiles + photo upload | Profile creation, photo storage (Cloudflare R2 — free 10GB) | 0 | W1-2
☐ | Discover / swipe system | Profile browsing, like/pass, match detection | 0 | W5-6
☐ | 1-to-1 video speed date | WebRTC via Jitsi, 5-min timer, all controls | 0 | W3-4
☐ | Lobby + queue system | Real-time presence, auto-session spin-up | 0 | W5-6
☐ | 5×5 group session engine | Session orchestration, rotation, survey, results | 0 | W5-6
☐ | Payment integration | Session purchase, Premium subscription, microtransactions | 0 | W7-8
☐ | Content moderation pipeline | NSFWJS for video, OpenAI for text, reporting system | 0 | W9-10
☐ | PWA optimization | Manifest, service worker, mobile touch UX, install prompt | 0 | W11
☐ | Load testing | Simulate 50 concurrent sessions on Hetzner | 0 | W11
APP STORES (POST-PWA)
☐ | Apple Developer enrollment | $99/year | 363 | W12
☐ | Google Play enrollment | $25 one-time | 92 | W12
☐ | Prepare App Store screenshots | 6.7" and 5.5" iPhone, Pixel screenshots | 0 | W12
☐ | Submit for review (Apple) | 17+ rating. Expect 1-3 rejections for dating apps | 0 | W12+
☐ | Submit for review (Google) | Content rating questionnaire. Usually faster than Apple | 0 | W12+
LAUNCH
☐ | Recruit 50 beta testers | Dubai Marina / JBR demographic. Influencer network | 5000 | W10
☐ | Soft launch (invite-only) | 50 users, 2 sessions/week, collect feedback | 0 | W11
☐ | Influencer seeding | 5-10 Dubai micro-influencers. Film session reactions | 10000 | W12
☐ | Public launch | Open waitlist, social media push, PR outreach | 0 | W12