## Executive Summary
PULSE ORBIT — UAE PILOT LAUNCH PLAN (REVISED)
Claude Code as primary developer ¦ Balanced tech stack ¦ All costs included
KEY METRIC | VALUE | UNIT | NOTES
Development Cost | 0 | AED | Claude Code — no dev hiring
Company Formation (IFZA) | 14000 | AED | Freezone license + visa + flexi-desk
Tech Stack (Year 1) | 2150 | AED | 14000
App Store Fees (Year 1) | 21756 | AED | Apple 30% / Google 15% on revenue
Marketing Budget (3 months) | 15000 | AED | Soft launch — influencer + social
Legal & Compliance | 8000 | AED | TRA registration + PDPL + T&C
Total Pre-Launch Investment | 39150 | AED | Sum of all one-time costs
Monthly Operational Cost | 642 | AED/mo | See Monthly Burn sheet
REVENUE MODEL
Subscription (Basic) | 49 | AED/mo | Group 5×5 access
Subscription (Premium) | 99 | AED/mo | 1-to-1 speed dates + group
Break-even Users (Basic) | 14 | users | Monthly cost / net revenue per user
Break-even Users (Premium) | 7 | users | Monthly cost / net revenue per user
LAUNCH COUNTRY
Corporate Tax | 9% |  | Only on profits > AED 375K
Personal Income Tax | 0%
Company Type | IFZA Freezone |  | 100% foreign ownership
Payment Processor | Tap Payments |  | 2.75% + AED 1 per txn
Video Provider | Daily.co |  | UAE-approved, WebRTC, $0.004/min
Backend | Supabase |  | Free tier → $25/mo at scale
Hosting | Vercel + Cloudflare |  | Free tier → $20/mo
Note on C5: Claude Code builds the product — zero dev cost

## Tech Stack
CATEGORY | RECOMMENDED | ALTERNATIVE | YEAR 1 (AED) | RATIONALE
Video Calling | Daily.co | Jitsi (self-hosted) | 500 | UAE-approved WebRTC. $0.004/min. Jitsi free but TRA risk + ops burden
Backend/DB | Supabase (free→Pro) | Pocketbase | 900 | Free tier covers MVP. Pro at $25/mo when scaling. Auth + DB + realtime built-in
Hosting (Frontend) | Vercel | Cloudflare Pages | 0 | Free tier sufficient. Already deployed. Auto-deploy from GitHub
Hosting (Backend) | Supabase Cloud | Hetzner VPS (€4.5/mo) | 0 | Included in Supabase plan. Hetzner for Jitsi if needed later
Payments | Tap Payments | PayTabs | 0 | 2.75% + AED 1/txn. No monthly fee. Better recurring billing API
SMS/OTP | Twilio Verify | AWS SNS | 400 | $0.05/verification. ~200 signups/mo × 12 = 2400 verifications
Email | Resend | Mailgun | 0 | Free tier: 3K emails/mo. Transactional only at MVP
Push Notifications | Firebase (FCM) | OneSignal | 0 | Free. Native web push + PWA support
CDN / Assets | Cloudflare R2 | AWS S3 | 0 | Free egress. 10GB free storage. Profile photos + assets
Analytics | Mixpanel | PostHog (self-host) | 0 | Free tier: 20M events/mo. Funnel + retention analysis
Error Monitoring | Sentry | LogRocket | 0 | Free tier: 5K events/mo. Critical for video call debugging
Domain + SSL | Cloudflare Registrar | Namecheap | 150 | ~$12/yr domain + free SSL via Cloudflare
AI Matching | OpenAI API | Claude API | 200 | Compatibility scoring. ~$15/mo at low volume
CI/CD | GitHub Actions | Vercel auto-deploy | 0 | Free tier: 2000 min/mo. More than enough
Monitoring | UptimeRobot | Better Uptime | 0 | Free tier: 50 monitors, 5-min checks
TOTAL YEAR 1 TECH COST |  |  | 2150 | Sum of all line items

## Dev Roadmap
WEEK | MILESTONE | DELIVERABLES | STATUS
1-2 | Auth + Profiles | Supabase auth, phone OTP, profile CRUD, photo upload to R2, basic matching algorithm | Pending
3-4 | Video Infrastructure | Daily.co integration, 1-to-1 video rooms, connection quality monitoring, auto-reconnect | Pending
5-6 | Matching Engine | Swipe/discover flow (live version), match notifications, accept/decline flow, queue management | Pending
7-8 | Group Sessions | 5×5 lobby system, round-robin pairing, timer management, session state machine | Pending
9 | Payments | Tap Payments integration, subscription tiers, webhook handlers, receipt generation | Pending
10 | PWA + Notifications | Service worker, offline shell, push notifications via FCM, app-like install prompt | Pending
11 | Admin + Analytics | Admin dashboard, Mixpanel events, session metrics, user reports, content moderation tools | Pending
12 | QA + Launch Prep | Load testing (video), security audit, TRA compliance check, app store listings, soft launch | Pending
| TOTAL DEVELOPMENT COST | AED 0 — Built entirely with Claude Code
| ESTIMATED TIMELINE | 12 weeks (part-time, evenings + weekends feasible)

## All Costs
COST ITEM | ONE-TIME (AED) | MONTHLY (AED) | YEAR 1 (AED) | NOTES
── COMPANY FORMATION ──
IFZA License | 10000 | 0 | 10000 | Digital services license
Visa (1 partner) | 3000 | 0 | 3000 | Residence visa processing
Flexi-desk (virtual office) | 0 | 0 | 1000 | Included in IFZA package
Emirates ID + Medical | 1500 | 0 | 1500 | Required for visa
── LEGAL & COMPLIANCE ──
TRA Registration | 3000 | 0 | 3000 | Telecom Regulatory Authority — VoIP app
PDPL Compliance (legal review) | 3000 | 0 | 3000 | Data protection assessment
Terms & Privacy Policy | 2000 | 0 | 2000 | Lawyer-drafted, UAE-compliant
Age Verification System | 0 | 0 | 0 | Built into auth flow by Claude Code
── TECH STACK ──
Video (Daily.co) | 0 | 42 | 500 | ~$11/mo at low volume
Backend (Supabase) | 0 | 0 | 0 | Free tier covers MVP phase
SMS/OTP (Twilio) | 0 | 33 | 400 | ~200 verifications/mo
Domain + SSL | 55 | 0 | 55 | ~$15 domain via Cloudflare
AI Matching (OpenAI) | 0 | 17 | 200 | GPT-4o-mini for compatibility
All other tech | 0 | 0 | 0 | Free tiers (Vercel, FCM, Sentry, etc.)
── APP DISTRIBUTION ──
Apple Developer Account | 370 | 0 | 370 | $99/yr
Google Play Developer | 92 | 0 | 92 | $25 one-time
Apple Commission (30%→15%) | 0 | 0 | 0 | Deducted from revenue, not a cost line
Google Commission (15%) | 0 | 0 | 0 | Deducted from revenue, not a cost line
PWA (Web — no commission) | 0 | 0 | 0 | Primary launch channel — zero take rate
── MARKETING (3-MONTH SOFT LAUNCH) ──
Instagram/TikTok ads | 0 | 3000 | 9000 | 3 months
Micro-influencers (Dubai) | 0 | 2000 | 6000 | 2-3 influencers/mo for 3 months
Launch event / meetup | 2000 | 0 | 2000 | One IRL event for credibility
── OPERATIONAL ──
Bank account maintenance | 0 | 50 | 600 | IFZA business bank account
Accounting / bookkeeping | 0 | 500 | 6000 | Outsourced, quarterly VAT filing
Customer support tool | 22870 | 0 | 0 | Free tier (Crisp or Tawk.to)
Misc / contingency | 2000 | 0 | 2000 | Buffer for unexpected costs
34295
TOTAL ONE-TIME COSTS
TOTAL MONTHLY COSTS
TOTAL YEAR 1 ALL-IN

## Monthly Burn
MONTHLY EXPENSE | AED/MONTH | NOTES
Video calling (Daily.co) | 42 | Scales with usage — $0.004/min
Backend (Supabase) | 0 | Free tier. $25/mo when >50K rows
SMS/OTP (Twilio) | 33 | ~200 verifications/mo
AI Matching (OpenAI) | 17 | GPT-4o-mini, ~$4.50/mo
Hosting (Vercel + CF) | 0 | Free tier
Email (Resend) | 0 | Free tier: 3K/mo
Push (Firebase) | 0 | Free
CDN (Cloudflare R2) | 0 | Free tier: 10GB
Analytics (Mixpanel) | 0 | Free tier: 20M events
Error monitoring (Sentry) | 0 | Free tier
Bank account | 50 | IFZA business bank
Accounting | 500 | Outsourced bookkeeping
TOTAL MONTHLY BURN | 642

## Launch Checklist
# | TASK | OWNER | DEADLINE | DEPENDENCY
1 | Register IFZA freezone company | Jamal | Week 1 | None
2 | Open business bank account | Jamal | Week 2 | #1 complete
3 | Register domain (pulseorbit.com) | Claude Code | Week 1 | None
4 | Set up Supabase project | Claude Code | Week 1 | None
5 | Build auth flow (phone OTP) | Claude Code | Week 1-2 | #4
6 | Build profile system + photo upload | Claude Code | Week 2 | #5
7 | Integrate Daily.co video rooms | Claude Code | Week 3-4 | #4
8 | Build matching/swipe engine | Claude Code | Week 5-6 | #6
9 | Build group 5×5 session system | Claude Code | Week 7-8 | #7, #8
10 | Integrate Tap Payments | Claude Code | Week 9 | #2 (bank)
11 | Build PWA + install prompt | Claude Code | Week 10 | #5-9
12 | Set up Firebase push notifications | Claude Code | Week 10 | #11
13 | TRA registration application | Jamal | Week 6 | #1
14 | PDPL compliance review | Lawyer | Week 8 | #6 (data flows defined)
15 | Draft Terms of Service | Lawyer | Week 8 | #14
16 | Age verification (Emirates ID / DOB) | Claude Code | Week 5 | #5
17 | Content moderation system | Claude Code | Week 11 | #7
18 | Admin dashboard | Claude Code | Week 11 | #4-9
19 | Mixpanel analytics integration | Claude Code | Week 11 | None
20 | Sentry error monitoring | Claude Code | Week 11 | None
21 | Load test video infrastructure | Claude Code | Week 12 | #7, #9
22 | Security audit (OWASP top 10) | Claude Code | Week 12 | All dev complete
23 | Apple Developer Account signup | Jamal | Week 10 | None
24 | Google Play Developer signup | Jamal | Week 10 | None
25 | PWA listing on app directories | Claude Code | Week 12 | #11
26 | Soft launch — invite 50 beta users | Jamal | Week 12 | All above
27 | Instagram/TikTok ad campaigns | Jamal | Week 13+ | #26 (feedback)
28 | Micro-influencer partnerships | Jamal | Week 13+ | #26
29 | Native iOS app (Capacitor wrap) | Claude Code | Week 14+ | #25 validated
30 | Native Android app (Capacitor wrap) | Claude Code | Week 14+ | #25 validated
31 | App Store submission | Jamal | Week 16+ | #29, #23
32 | Play Store submission | Jamal | Week 16+ | #30, #24

## Country Comparison
FACTOR | UAE (DUBAI) | SAUDI ARABIA | SINGAPORE | UK | TURKEY
Corporate Tax | 9% | 15% | 17% | 25% | 25%
Income Tax | 0% | 0% | 0-22% | 20-45% | 15-40%
Company Setup Cost | ~$4K | ~$3K | ~$3K | ~$200 | ~$500
Company Setup Time | 2 weeks | 1-2 weeks | 1-2 days | 1 day | 1 week
Target Population | 10M | 35M | 5.8M | 67M | 85M
Expat % (dating TAM) | 85% | 38% | 29% | N/A | N/A
Dating App Competition | Medium | Low | Very High | Very High | High
Willingness to Pay | Very High | High | High | Medium | Low
Regulatory Risk | Medium | High | Low | Low | Medium
VoIP Regulation | Requires TRA | Restricted | Open | Open | Open
Payment Infra | Strong | Strong | Strong | Strong | Moderate
English Proficiency | Very High | Moderate | Very High | Native | Low
Marketing Cost (CPM) | Medium | Low | Very High | High | Low
VERDICT | LAUNCH HERE | Market #2 | Skip | Skip | Skip